## Infrastructure Proposal
Project | Product | Description | Qty | Locations | Price Each | Total Cost | Support Included | Cost of Support Thereafter | Time Frame | Total Days
External DNS | InfoBlox Appliance | Replacement of 9 year old external DNS servers running on Optiplex 110. Redundant secure solution with one appliance at CHC and SBVC. | 2 | CHC, SBVC | 10320.39 | 20640.78 | 3 years | $6,590/ 3 Years | 05/03/2010 - 05/14/2010 | 10 Days
Compellant SANs | Compellant | Storage Area Network (SAN) solution for CHC\SBVC\District; fully redundant; 30TB total disk space; Single mailbox restore; Snapshots; Site-to-site replication. | 3 | CHC, SBVC, District | Varies by Site | 358295.34 | 3 years | $27,294/ 3 Years | 05/17/2010 - 06/11/2010 | 20 Days
Virtualization | Dell VMWare | Replacement of current server hardware with Dell Blade\VMWare virtual environment; fully redundant locally and between sites. | 1 | CHC, SBVC, District | 114029.78 | 114029.78 | 3 - 5 Years | $18,297/ 3 Years; $24,197/ 5 Years | 06/16/2010 - 12/31/2010 | 143 Days
Data Center Power | Computer Protection Technologies | Complete refresh of SBVC and CHC data center power systems | 2 | CHC, SBVC | 18394.42 | 36788.83 | 1 Year | $2,300/ Year | 05/03/2010 - 05/11/2010 | 7 Days
Firewalls | Fortigate | Replacement of PIX 525s with redundant firewalls for CHC and SBVC, 10GB ready, reporting, VPN, NAC. | 4 | CHC, SBVC | 66696.56 | 266786.24 | 1 Year | $8,423/ Year | 10/13/2010 - 11/23/2010 | 30 Days
Datatel Production Server | HP | Removal of test and developments off of the production Datatel Server and on to a dedicated server/hardware. | 1 | Old to CHC, new to SBVC | 795555.03 | 795555.03 | 3 years | $174,389/ 3 Years | 01/03/2011 - 02/11/2011 | 30 Days
Switching Backbone | Extreme | Replacement of two 6509 backbone switches. Speed increase to 10GB, new supervisors, current IOS | 2 | SBVC | 100877.55 | 201755.1 | 1 Year | $28,340/ Year | 01/24/2011 - 03/25/2011 | 45 Days
Switching Edge | Extreme | Replacement of old edge switches | 54 | CHC, SBVC, District | 13936.97 | 752596.2 | Lifetime | $0 | 06/01/2011 - 10/04/2011 | 90 Days
[5 empty] | Total Cost | 2546447.3 |  |  | Total Time | 375

## Support
Project | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7
External DNS | 0 | 0 | 0 | 6590 | 0 | 0 | 0
SANs | 0 | 0 | 0 | 27294 | 0 | 0 | 0
Virtualization | 0 | 0 | 0 | 18297 | 0 | 24197 | 18297
Power | 0 | 2300 | 2300 | 2300 | 2300 | 2300 | 2300
Firewalls | 0 | 84230 | 84230 | 84230 | 84230 | 84230 | 84230
Datatel | 0 | 0 | 0 | 174389 | 0 | 0 | 0
Switching | 0 | 28340 | 28340 | 28340 | 28340 | 28340 | 28340
Total Maintenance | 0 | 114870 | 114870 | 341440 | 114870 | 139067 | 133167